DOCUMENT

# Research Plan for UX Research

Plan de investigación

Internal version. It includes the team's assumptions, risks and budget. The version shared with the client omits sections 8 and 9.

## 1. Project details

| Field | Value |
| --- | --- |
| Client | [Client name] |
| Project | [Onboarding for a personal finance app] |
| Lead | [Name · role] |
| Client contact | [Name · role] |
| Field window | [DD/MM/YYYY – DD/MM/YYYY] |
| Status | [Draft · In review · Approved] |
| Template version | v1.0 · last reviewed [DD/MM/YYYY] · see the original at UXR |

## 2. Problem and context

The app has high drop-off during sign-up. The team knows people leave, but not at which step or why. Product data shows the aggregate drop; it does not explain the decision to close the app.

What we already know: [overall drop-off rate], [step with the largest drop according to analytics], [related support tickets].

What we do not know: what information the user is missing at each step, what creates distrust, and whether the drop-off is final or postponed.

The decision that depends on this: [redesign the bank-linking step vs. reorder the sign-up sequence], with a decision date of [DD/MM].

## 3. Research questions

| # | Question | Method | Deliverable |
| --- | --- | --- | --- |
| Q1 | Which step do they stop at, and what are they thinking there? | Interviews with a guided walkthrough | Findings and severity matrix |
| Q2 | What information does the app ask for that the person does not have at hand? | Interviews + heuristic review | Heuristic report |
| Q3 | How widespread is distrust about linking a bank account? | Survey of the installed base | Survey report |

Three questions at most. If a fourth appears, something is out of scope or it is a different project.

## 4. Method

### 4.1 Stage, and what goes in front of the participant

Evaluative and formative: sign-up already exists and we want to know why it
fails before redesigning it, not to measure how much it improved afterwards.

What goes in front of them: the sign-up flow in production, on the
participant's own phone. No prototype: the problem is in what is already shipped.

### 4.2 Design

Qualitative first, quantitative after. [10] semi-structured interviews of [60] min with a guided walkthrough on the participant's device, remote over video call with screen sharing. Then a [8]-question survey to [n] users of the installed base, to size the patterns found.

### 4.3 Why this method and not another

A classic usability test would measure whether the task is completed; we already know it is not. What is missing is the reason, and that shows up in conversation during the walkthrough. The survey alone is no use yet: we do not know what to ask.

### 4.4 Logistics

Remote, moderated, over video call with screen sharing. Remote because the
segment is spread across several cities; moderated because the question is why,
and that gets asked in the moment.

### 4.5 Instruments

- Recruitment screener — [link]

- Interview guide (internal and participant versions) — [link]

- Findings and severity matrix — [link]

- Informed consent — [link]

## 5. Sample and recruitment

| Criterion | Definition | Quota |
| --- | --- | --- |
| Abandoned sign-up | Downloaded and did not complete activation, last 60 days | 6 |
| Completed sign-up | Activated the account, last 60 days (contrast group) | 4 |
| Variable income | Self-employed, freelance or invoicing per job | min. 4 |
| Exclusion | Works in banking, fintech, design or research | — |

Recruitment: [own panel / client's base / agency]. Incentive [amount] per session. Over-recruit [20%] for no-shows.

## 6. Timeline

| Stage | Dates | Owner | Needed from the client |
| --- | --- | --- | --- |
| Design and instruments | [week 1] | [UXR] | Plan approval |
| Recruitment | [weeks 1–2] | [UXR] | Access to the user base |
| Fieldwork | [week 3] | [UXR] | A stable test environment |
| Analysis | [week 4] | [UXR] | — |
| Delivery and workshop | [week 5] | [UXR + client] | Product team attendance |

## 7. Deliverables

- Insights presentation ([n] slides) with prioritized recommendations.

- Findings and severity matrix, with estimated effort.

- Customer journey map of the activation process.

- [90] min handover workshop with the product team.

## 8. Assumptions and risks

Internal only

| Risk | Likelihood | Mitigation |
| --- | --- | --- |
| We cannot reach the people who abandoned sign-up | High | External recruitment with our own screener |
| The test environment goes down during the walkthrough | Medium | Backup Figma prototype with the same steps |
| The team expects drop-off figures from the qualitative part | High | An explicit method note in the delivery and in the workshop |

## 9. Budget and hours

Internal only

| Item | Hours | Amount |
| --- | --- | --- |
| Design and instruments | [ ] | [ ] |
| Fieldwork ([10] sessions) | [ ] | [ ] |
| Incentives | — | [ ] |
| Analysis and delivery | [ ] | [ ] |
| Total | [ ] | [ ] |

## 10. Method note and limitations

With [10] interviews the findings describe reasons and mechanisms, not proportions of the population. The follow-up survey sizes them; the qualitative part explains them. No number from the qualitative phase is presented as a percentage. The group that completed sign-up is included as a contrast, not as a representative sample of active users.

UXR SpA · User research [contacto@uxr.cl] · [uxr.cl]

Template v1.0 · reviewed [DD/MM/YYYY] Original at UXR — check that your copy has not expired

## License and attribution

Template by UXR SpA · Paulina Contreras · version 1.0

Published under Creative Commons Attribution 4.0 International (CC BY 4.0):
https://creativecommons.org/licenses/by/4.0/

You may use it, adapt it and use it in paid work, including commercially, as
long as you credit the authorship and link to uxr.cl.

The license covers this template. The document you complete with it is yours and
is not covered: your study's data and your participants' data are yours.

Original, usage context and legal grounding: https://uxr.cl/en/templates/research-plan/
Check that your copy is not out of date.